## Лист1
Agreed requirements (second edition) | Сlarification of requirement | The requirement is covered by the test cases during smoke-testing of MVP model (covered, not covered, partly covered) | Test cases covering requirements during smoke-testing of MVP model, it's status (№) | The requirement is satisfied, not satisfied, partly satisfied | Problems and disagreements of MVP model and agreed requirements | Recommendations and options for correction | Comments
Requirement №1 Web hosting must provide the following parameters for stable operation:
1.1 Portal uptime 99%. | n\a | not covered | n\a | n\a | n\a | n\a
1.2 The hosting portal must have geographically distributed data centers on at least two continents (American and European). | n\a | not covered | n\a | n\a | n\a | n\a
1.3 Availability of the support team 24/7 with the possibility of contacting via service tickets with priority. | n\a | not covered | n\a | n\a | n\a | n\a | MVP model includes the support form and the chatbot, though requirement 1.3 provides only support team 24/7 with the possibility of contacting via service tickets with priority
Requirement №2 A mobile version of the portal or a mobile application that can work on mobile devices with support for Android and IOS operating systems and in browsers compatible with these mobile operating systems.
2.1 Тhe mobile version of the portal must be adapted for Chrome and Mozilla browsers for the Android operating system. | n\a | not covered | n\a | n\a | n\a | n\a
2.2 Тhe mobile version of the portal must be adapted for the Safari browser for the IOS operating system. | n\a | not covered | n\a | n\a | n\a | n\a
Requirement №3 The design of the portal should be related to the theme of the web-portal and be able to update elements through the CMS console.
3.1 The CMS of the portal should be able to develop (implement) any design that the customer needs. | n\a | not covered | n\a | n\a | n\a | n\a
3.2 All mockups must correspond to the relevant theme of the web-portal. | n\a | covered | Test case № 3.1, failed Test case № 3.2, failed Test case № 3.3, failed Test case № 3.4, failed Test case № 3.5, failed Test case № 3.6, failed Test case № 3.7, failed Test case № 3.8, failed Test case № 3.9, failed Test case № 3.10, failed Test case № 3.11, failed Test case № 3.12, failed Test case № 3.13, failed Test case № 3.14, failed Test case № 3.15, passed | not satisfied | MVP model has mockups that does not correspond to the relevant theme of the web-portal and show another mode of transport. Section "Shop" does not work, has some errors, inaccuracies and duplications | Change the MVP model's mockups to mockups that correspond to the relevant theme of the web-portal - selling and servicing electric scooters, fix errors, inaccuracies and duplications | 1. Every product's page has the opportunity to share the link it's product through social media: Pinterest, Twitter, Facebook and WhatsApp Messenger. The requirements do not provide for this option. 2. MVP model has "Subscribe Form". The requirements do not provide for this option.
Requirement №4 The work of the front end of the portal should be based on the following requirements:
4.1 Responsive design. The portal should be responsive to different screen sizes, including mobile devices, tablets and desktop computers. | n\a | not covered | n\a | n\a | n\a | n\a
4.2 The possibility of adding photos in jpg and png formats up to 5 megabytes. | n\a | not covered | n\a | n\a | n\a | n\a
4.3 Тhe ability to update the portal for users without a deep understanding of the frontend | Only administrator must update the portal adding new goods | not covered | n\a | n\a | n\a | n\a
Requirement №5 Stable operation of the backend of the portal.
5.1 Portal uptime is 99%. 1% of service time is paid extra. | n\a | not covered | n\a | n\a | n\a | n\a
5.2 Only update the system after coordination with the site staff. | n\a | not covered | n\a | n\a | n\a | n\a
5.3 The user base should be multi-level (2 copies for backup). | n\a | not covered | n\a | n\a | n\a | n\a
5.4 SQL database backup should be performed once a day. | n\a | not covered | n\a | n\a | n\a | n\a
5.5 Database administration should be performed by the staff of the hosting provider. | n\a | not covered | n\a | n\a | n\a | n\a
Requirement №6 Fast registration process.
6.1 Order by phone number in the form of a quick form. | n\a | covered | Test case № 6.1, failed Test case № 6.2, failed Test case № 6.3, failed Test case № 6.4, failed Test case № 6.5, passed Test case № 6.6, passed Test case № 6.7, failed Test case № 6.8, passed Test case № 6.9, failed | not satisfied | MVP's model shopping card does not work correctly: price per piece changed according to numder of pieces, it is possible to exceed number of pieces, total value of the items does not include taxes and shipping, when changing the delivery address, shipping price is not changed, quick form does not need a phone number | Fix the mistakes when calculating goods
6.2 The usual order form through registration by phone number and email. | First user needs to register. Perhaps registration form should have "Login", "Password", "Phone number" and "Email" | covered | Test case № 6.10, failed Test case № 6.11, failed | not satisfied | MVP's model sign up form appears with an offer to sign up with Google or Facebook or email, registration is not correct | Change the way of registration to using the phone number and email
6.3 Feedback form about registration using Whatsapp or SMS. | n\a | not covered | n\a | n\a | n\a | n\a
Requirement №7 User safety and secure payments.
7.1 Information about bank cards attached to the account must be stored in the database of the online store in an encrypted form. | n\a | not covered | n\a | n\a | n\a | n\a
7.2 The main portal page must use the https protocol with an up-to-date SSL certificate. | Perhaps main portal page must use the https protocol with an up-to-date TLS certificate | covered | Test case № 7.1, failed | not satisfied | MVP's model main portal page uses the QUIC protocol with equivalent certificate to TLS certificate | n\a
7.3 Internal pages of the portal must support the https protocol with an up-to-date SSL certificate. | Perhaps internal pages must use the https protocol with an up-to-date TLS certificate | covered | Test case № 7.2, failed | not satisfied | MVP's model internal portal pages uses the QUIC protocol with equivalent certificate to TLS certificate | n\a
7.4 User authentication can occur using the portal's authorization elements. | Perhaps authentication form should have "Login", "Password" | not covered | n\a | n\a | n\a | n\a
7.5 Integration with Apple Pay and Google Pay payment systems. | n\a | not covered | n\a | n\a | n\a | n\a
Requirement №8 Information about each model of electric transport should be with a detailed description.
8.1 The web-portal should contain information about each model with a detailed technical description. | n\a | covered | Test case № 8.1, failed Test case № 8.2, failed Test case № 8.3, failed Test case № 8.4, failed Test case № 8.5, failed Test case № 8.6, failed Test case № 8.7, failed Test case № 8.8, failed Test case № 8.9, failed Test case № 8.10, failed | not satisfied | MVP model has the technical information is in Ukrainian language and it is not full, has mistakes in the words, elements of page is in Ukrainian language, articles are not correct, prices is in hryvnias, the general information is available but is not formatted and not always exists | Fix the mistakes and bring it into the line with the main theme of web-portal
8.2 Users should have the option (feedback form) if the technical specifications are incorrect. | First user needs to register and then give a feedback. Feedback form should have fields "Login", "Subject", "Message", "Priority" | covered | Test case № 8.11, failed Test case № 8.12, failed | not satisfied | MVP's model support form has fields "First name", "Last name", "Email", "Phone" , "Choose an issue", "Let us know what you need help with..." that are not correspond to requirement | Change fields "First name", "Last name", "Email", "Phone" , "Choose an issue", "Let us know what you need help with..." to the "Login", "Subject", "Message", "Priority" | MVP model has section "Contact" on the header that inclueds contact form with fields "Name", "Email", "Subject", "Message". The contact form duplicates the support form. Perhaps the contact form should include contact data sales' department and service's department
Requirement №9 The web-portal should have the possibility to sign up for a test drive.
9.1 The registration form does not allow users under the age of 13 to register for a test drive (age validation). | n\a | not covered | n\a | n\a | n\a | n\a
9.2 The test drive registration form allows anyone to register using a phone number. | First user needs to register and then sign up for a test drive using fields "Login", "Data", "Devise's model" | covered | Test case № 9.1, failed | not satisfied | MVP's model signing up for service is still closed | If his service is still closed MVP model shoul not contain this card
Requirement №10 The possibility of registration in the service center of those users who have already purchased the product (model).
10.1 Registration form in the service center of buyers who need product warranty support. | First user needs to register | not covered | n\a | n\a | n\a | n\a
10.2 The possibility of a quick registration form for a non-warranty (paid repair) service using a phone number. | First user needs to register | not covered | n\a | n\a | n\a | n\a
10.3 Registration form for non-warranty service for users who purchased a product (supported model) from another supplier. | First user needs to register | not covered | n\a | n\a | n\a | n\a
Requirement №11 Product reviews.
11.1 Feedback can be provided by any registered user. | First user needs to register | not covered | n\a | n\a | n\a | n\a
11.2 The product rating scale must be present in each item, scale from 1 to 10 (star) | n\a | not covered | n\a | n\a | n\a | n\a
11.3 The rating scale of the product affects its rating (model). | n\a | not covered | n\a | n\a | n\a | n\a
Requirement №12 Individual product recommendations.
12.1 Users who have already purchased the product - receive an informational newsletter with recommendations to the registered number in case of any promotion with the possibility of unsubscribing (restriction of the newsletter). | First user needs to register | not covered | n\a | n\a | n\a | n\a
12.2 Users who registered the purchased product on the site receive a reminder about the end of warranty support. | First user needs to register | not covered | n\a | n\a | n\a | n\a
12.3 Users who have registered, but have not yet purchased the product - receive a message about the viewed product. | First user needs to register | not covered | n\a | n\a | n\a | n\a
12.4 Users who have registered, but put the product in the basket - receive a reminder to pay for this product. | First user needs to register | not covered | n\a | n\a | n\a | n\a
Requirement №13 Integration of the portal with video hosting for viewing video reviews of products (models).
13.1 The portal must be integrated with YouTube video hosting. | n\a | covered | Test case № 13.1, passed | satisfied | n\a | n\a
13.2 The video hosting channel where the reviews are posted has private access for editing and adding videos from the site owners. | n\a | not covered | n\a | n\a | n\a | n\a
13.3 Each user who purchased a product (a certain model) can leave a video about unpacking by sending a link to the portal administrator. | First user needs to register | not covered | n\a | n\a | n\a | n\a
Requirement №14 The portal must have the technical capability to implement analytics tools.
14.1 It is necessary to ensure the integration of the portal to work with SEO tools. | n\a | not covered | n\a | n\a | n\a | n\a
14.2 Portal analytics and statistics should be done with the help of the marketing team and/or business analysts. | n\a | not covered | n\a | n\a | n\a | n\a
14.3 A SEO specialist can get developer support to solve issues with the integration of their own statistics collection tools. | n\a | not covered | n\a | n\a | n\a | n\a